**SDM 635 – Bank St (Care Clinics)**

**Start Date – June 16th**

**Week of June 16th to June 20th**

* Demo to begin
* Steel stud framing to begin

**Week of June 23rd – June 27th**

* Plumbing Rough In to begin
* Concrete cutting to be completed
* Steel Stud Framing to be completed

**Week of June 30th – July 4th**

* Hvac rough In
* Plumbing rough in to continue, inspection this week.

**Week of July 7th – July 11th**

* Drywall install to begin
* Drywall taping to begin
* Sprinkler Rough In
* IT Rough in July 7th

**Week of July 14th – July 18th**

* Drywall taping to be completed
* Hardstop panels to be installed
* Flooring to be completed
* Sprinkler Finishing

**Week of July 21st – July 25th**

* July 21st Fixture Delivery and Install
* July 23rd Plumbing Finishing

**Week of July 28th – August 1st**

* Finishing and clean up
* Speaker Install July 28th
* Hardware Install July 31st
* Icon Digital – July 31st

**Soft Opening – August 7th**